## How to use
Mystery Shopper Improvement Tracker
Purpose: track every improvement point from Mystery Shopper reports until it is fixed and checked. Set up after the QA internal audit (auditor: Dr. Shen, September 2026).
THE CYCLE (every report)
1. New report | Log it in 'MS Reports'. Then add each improvement point to 'Tracker' (one row per point). Status = Open.
2. Review meeting | For each Open point, agree the action plan, PIC, priority and timeline. Type the 'Date agreed'. The target date fills in by itself.
3. Follow up | At every meeting, update Status and Progress. Look at the Alert column first: red OVERDUE, then amber Due soon.
4. Done | When the action is finished, set Status to 'Done - to verify'. Fill in Date completed and Evidence (e.g. SOP updated, training attendance, new WhatsApp template).
5. Verify & close | Check the next Mystery Shopper report for that outlet. Not mentioned again: set Status to 'Closed' and fill in Verified by / date. Mentioned again: set it back to 'In progress' and revise the plan.
6. Record the meeting | Add one row in 'Meeting Log' (date, attendees, IDs reviewed, decisions).
PRIORITY & TIMELINE GUIDE (agree the real timeline at the meeting)
High | Affects trust or whether the customer comes back (e.g. sales pressure, long waiting). Aim: within 2 weeks.
Medium | Affects comfort or clarity (e.g. treatment steps, technique). Aim: within 1 month.
Low | Small preference or quick fix (e.g. reminder by WhatsApp). Aim: within 1 to 2 months.
STATUS
Open | Logged, no action agreed yet.
In progress | Action plan agreed and being done.
Done - to verify | Action finished. Waiting for the next MS report to confirm it worked.
Closed | Verified: the problem did not come back. The row turns grey.
On hold | Paused on purpose (write the reason in Remarks).
ALERT COLUMN (automatic)
OVERDUE | Target date has passed and it is not done yet. Discuss first.
Due soon | Target date is within the next 7 days.
On track | Target date is more than 7 days away.
Set target | No target yet: pick a timeline and date agreed.
CELLS
White | Type here.
Grey | Automatic (formulas). Don't type, except the target date if you need a custom date.
ID FORMAT
MS-YYMM-OUTLET-NN e.g. MS-2609-CLM-01 = Mystery Shopper, Sep 2026, Cheras Leisure Mall, point 1. Outlet codes are in the Lists sheet (GL, PC, CLM).
EXAMPLE ROW (example only, not real data: shows how a finished row looks)
ID | MS-2610-PC-01
Outlet | Puchong
Improvement point | Customer not reminded of simple actions during treatment
Priority | Medium
Agreed action plan | Add 3 short cue phrases to the therapist script; brief all therapists at the morning huddle
PIC | Therapist Lead
Date agreed / Timeline | 01/10/2026 · 2 weeks → Target date 15/10/2026 (auto)
Status / Progress | Done - to verify · Script updated 07/10; all 4 therapists briefed 08/10
Evidence | Updated script v2 + huddle attendance sheet
How to verify | Next MS report for Puchong: point not mentioned again

## Tracker
Mystery Shopper Improvement Tracker
One row per improvement point. White cells: type here. Grey cells: automatic, don't type. Set up after the QA internal audit (auditor: Dr. Shen) to track each Mystery Shopper improvement point until it is fixed and verified.
① FEEDBACK (from the Mystery Shopper report) | [7 empty] | ② ACTION PLAN (agree at the review meeting) | [5 empty] | ③ FOLLOW-UP (update at every review) | [5 empty] | ④ VERIFY & CLOSE
ID | Outlet | Improvement point | MS report (month) | Category | What the customer said | Customer's original words | Suggested action (from report / draft) | Priority | Agreed action plan | PIC | Date agreed | Timeline | Target date (auto) | Status | Days left (auto) | Alert (auto) | Progress update / action taken | Date completed | Evidence | How to verify | Verified by | Verified date | Remarks
MS-2609-CLM-01 | Cheras Leisure Mall | Package presentation felt too commercial | Sep 2026 | Sales & package | Customer was first shown a full treatment journey above RM20,000, then a package recommendation. She felt pressured and the number itself was intimidating. This is the main reason her revisit answer was only "Maybe". | “先给我看整个疗程2万多，然后推荐配套。过程有点压力，也被数值吓到。如果有菜单直接看更好。” | Show a simple treatment menu early, before any package talk, to reduce sticker shock and make options easier to understand. | High | [5 empty] | Open |  | Set target |  |  |  | Next MS report: customer does not mention sales pressure; revisit answer improves. |  |  | Same theme as MS-2609-GL-01 (consultant sales approach).
MS-2609-CLM-02 | Cheras Leisure Mall | Customer had to keep confirming the RM399 trial | Sep 2026 | Sales & package | Customer needed to confirm several times that she was doing the RM399 trial. Clear reassurance at the start would help her feel secure. | “我需要反复确认是不是给我399trial配套，他们可能可以说我今天是做这个价钱，让我安心。” | Confirm today's RM399 trial clearly at the start, before any upgrade conversation. | High | [5 empty] | Open |  | Set target |  |  |  | Next MS report for Cheras Leisure Mall: this point is not mentioned again.
MS-2609-CLM-03 | Cheras Leisure Mall | Treatment steps were not clear | Sep 2026 | Communication | She heard a lot about acne-scar packages but was not clear on the steps for that visit. After the laser she thought it was finished, then learned there was a hydration treatment too. | “在开始疗程的时候我不清楚我的疗程的步骤……做完laser我以为完了，医生告诉我还有补水护理。” | Brief the full treatment flow from start to finish before treatment starts. | Medium | [5 empty] | Open |  | Set target |  |  |  | Next MS report for Cheras Leisure Mall: this point is not mentioned again.
MS-2609-CLM-04 | Cheras Leisure Mall | Long waiting time (about 1pm to 4pm) | Sep 2026 | Waiting & process flow | Customer stayed about 3 hours. Waiting at face washing / photos, doctor, payment (bill printing) and account setup. | “整体时长我在那边呆了1pm到差不多4pm，感觉时间比较久……尤其是付款等打单等了蛮久。” | Tighten handoffs between washing, photos, doctor, payment and registration. | High | [5 empty] | Open |  | Set target |  |  |  | Next MS report: total visit time is shorter and waiting is not mentioned.
MS-2609-CLM-05 | Cheras Leisure Mall | Registration code sent without explanation | Sep 2026 | Registration & system | A code was sent for account registration without first explaining why. The customer found it strange until the purpose was clarified. | “有人来说要拿code注册账号，一开始没和我解释是为了这个目的……我感到奇怪。” | Explain why the customer is receiving the code before sending it. | Low | [5 empty] | Open |  | Set target |  |  |  | Next MS report for Cheras Leisure Mall: this point is not mentioned again.
MS-2609-CLM-06 | Cheras Leisure Mall | Therapist hand technique felt firm | Sep 2026 | Treatment & technique | Therapist explained the steps and cared for the customer (offered to switch off the light), but the hand technique felt slightly firm. | “护理小姐姐的手法可以再进步，手法不够柔。” | Use a gentler, more relaxing hand technique (refresher training). | Medium | [5 empty] | Open |  | Set target |  |  |  | Next MS report for Cheras Leisure Mall: this point is not mentioned again.
MS-2609-CLM-07 | Cheras Leisure Mall | Prefers WhatsApp reminder instead of a call | Sep 2026 | Appointment & reminder | Outlet proactively sent the address and called the day before (good). But the customer was at work and would prefer a WhatsApp reminder. | “前一天会call。不过我在工作，希望whatsapp reminder就好。” | Draft: ask customers their preferred reminder method (WhatsApp or call) and follow it. | Low | [5 empty] | Open |  | Set target |  |  |  | Next MS report for Cheras Leisure Mall: this point is not mentioned again.
MS-2609-GL-01 | Greenlane | Service attitude dropped when customer could not afford the high-price package | Sep 2026 | Service attitude | Customer felt clear snobbery and discrimination because she had no credit card and a limited budget. After staff learned she could not buy the high-price package (RM30k), their service attitude dropped and she was disappointed. She asked why there were no other options based on the customer's needs, instead of only pushing high-price packages. In her follow-up message she said it was not only the selling: mainly the attitude made her uncomfortable. She added that young staff lacking experience is understandable, as long as they are willing to improve. | “感受到有明显的势利感和歧视倾向（因为我没有信用卡而且预算有限），服务员在得知无法消费高额配套(RM 30k)，而产生服务态度的落差，有点失望。怎么就没有其他选择‘满足客户需求’为导向，而非一味推销高价配套呢！” Follow-up: “其实当天不完全是因为推销的问题，主要是态度，让人感觉不太舒服。” | Draft: coach the consultation team to keep the same warm service whatever the customer's budget, and to offer options that fit the customer's needs and budget instead of only high-price packages. | High | [5 empty] | Open |  | Set target |  |  |  | Next MS report for Greenlane: no comments on attitude or sales pressure; customer is offered options within budget. |  |  | Same theme as MS-2609-CLM-01 and -02 (consultant sales approach). Feedback received 15/09/2026.
Formulas:
Days left (auto) = IF(OR([Target date (auto)]="",[Status]="Closed",[Status]="Done - to verify"),"",[Target date (auto)]-TODAY())
Alert (auto) = IF([Improvement point]="","",IF([Status]="Closed","Closed",IF([Status]="Done - to verify","To verify",IF([Status]="On hold","On hold",IF([Target date (auto)]="","Set target",IF([Target date (auto)]<TODAY(),"OVERDUE",IF([Target date (auto)]-TODAY()<=7,"Due soon","On track")))))))
Note on I4: Prefilled priorities are suggestions. Confirm them at the review meeting.
Note on M4: Pick a timeline and fill in 'Date agreed'. The target date calculates itself. Need a different date? Just type it over the target date.
Note on O4: Open → In progress → Done - to verify → Closed. Only close after checking the next Mystery Shopper report.

## Dashboard
Dashboard: Mystery Shopper improvement points
Updates automatically from the Tracker sheet. Nothing to type here.
Today: | 2026-09-29
Total points | Open | In progress | To verify | Closed | OVERDUE | Due in 7 days | % closed
8 | 8 | 0 | 0 | 0 | 0 | 0 | 0%
By outlet
Outlet | Total | Open | In progress | To verify | Closed | OVERDUE | % closed
Greenlane | 1 | 1 | 0 | 0 | 0 | 0 | 0%
Puchong | 0 | 0 | 0 | 0 | 0 | 0
Cheras Leisure Mall | 7 | 7 | 0 | 0 | 0 | 0 | 0%
By priority
Priority | Total | Open | In progress | To verify | Closed | OVERDUE | % closed
High | 4 | 4 | 0 | 0 | 0 | 0 | 0%
Medium | 2 | 2 | 0 | 0 | 0 | 0 | 0%
Low | 2 | 2 | 0 | 0 | 0 | 0 | 0%
By category
Category | Total | Open | In progress | To verify | Closed | OVERDUE | % closed
Sales & package | 2 | 2 | 0 | 0 | 0 | 0 | 0%
Service attitude | 1 | 1 | 0 | 0 | 0 | 0 | 0%
Communication | 1 | 1 | 0 | 0 | 0 | 0 | 0%
Waiting & process flow | 1 | 1 | 0 | 0 | 0 | 0 | 0%
Treatment & technique | 1 | 1 | 0 | 0 | 0 | 0 | 0%
Appointment & reminder | 1 | 1 | 0 | 0 | 0 | 0 | 0%
Registration & system | 1 | 1 | 0 | 0 | 0 | 0 | 0%
Environment & facilities | 0 | 0 | 0 | 0 | 0 | 0
Others | 0 | 0 | 0 | 0 | 0 | 0

## MS Reports
Mystery Shopper reports received
Log every report here when it arrives, then copy its improvement points into the Tracker. Grey columns are automatic.
Report ID | MS report (month) | Outlet | Visit date | Score (as reported) | Would return / recommend? | Points logged (auto) | Points closed (auto) | Staff named in report | Report file | Reviewed at meeting | Notes
MS-2609-CLM | Sep 2026 | Cheras Leisure Mall |  | 93 | Maybe / Yes. Price is expensive, but may return for pigmentation treatment. | 7 | 0 | Dr. Agnes Lu, Alice, Ng Kai Wei, Irene | MS result sheet (Sep, Cheras Leisure Mall row) + UR_Klinik_Mystery_Shopper_Cheras_Leisure_Mall_September_Feedback_Appendix.pptx |  | Main theme: package presentation felt too commercial; long waiting; treatment steps not clear.
MS-2609-GL | Sep 2026 | Greenlane |  | 60 | Maybe / Maybe / Still considering… | 1 | 0 | Dr Michelle, Stella, Karene, Graceyy | MS result sheet (Sep, Greenlane row) + customer's WhatsApp follow-up, 15/09/2026 |  | Customer's follow-up: the main issue was staff attitude, not only the selling. Staff mentioned in the QA chat: Dr Michelle and Stella.

## Meeting Log
Review meeting log
One row per review meeting: this is your record for the next audit.
Meeting date | Attendees | Tracker IDs reviewed | Decisions / key notes | Next review date
MS-2609-CLM-01 to 07, MS-2609-GL-01

## Lists
Dropdown lists: add new outlets, categories or PIC names in the empty cells below each list.
Outlets | Outlet code (for ID) | Categories | Priority | Status | PIC (person in charge) | Timeline | Days
Greenlane | GL | Sales & package | High | Open | Outlet Manager | 1 week | 7
Puchong | PC | Service attitude | Medium | In progress | Front Desk / CS | 2 weeks | 14
Cheras Leisure Mall | CLM | Communication | Low | Done - to verify | Doctor | 1 month | 30
|  | Waiting & process flow |  | Closed | Therapist Lead | 2 months | 60
|  | Treatment & technique |  | On hold | Sales / Consultant | 3 months | 90
|  | Appointment & reminder |  |  | QA
Registration & system
Environment & facilities
Others